## Status Report
Project Plan
|  | Project Name | [5 empty] | Setra - Infor10 SCE Implementation | [9 empty] | SNS Project Manager | [5 empty] | Bernard Khazzaka | [6 empty] | Operational Lead | [5 empty] | Paul Saade
|  | Project Sponsor | [5 empty] | Rabie Raad / Hamza Dakkak | [9 empty] | SNS Business Manager | [5 empty] | Mario Ghosn | [6 empty] | Report Date | [5 empty] | 2015-03-19
Project Phases |  |  |  | Status |  |  |  |  | Project Highlights
I | Project Initiation |  |  | Completed |  |  |  |  | SOP document sent to Setra on Thursday March 19
II | Business Review Summit |  |  | In Progress |  |  |  |  | Super User training will be conducted by SNS from 20-04-2015 till 23-04-2015
III | Deployment and UAT |  |  | Not Started |  |  |  |  | UAT will be conducted by SNS from 26-04-2015 till 29-04-2015
IV | Go-Live |  |  | Not Started |  |  |  |  | End user training will be conducted by Setra from 30-04-2015 till 07-05-215
V | Project Closure |  |  | Not Started |  |  |  |  | Stock count will be conducted by Setra from 09-05-2015 till 13-05-2014
Project Health Indicators |  |  |  | Period Ending
On Track |  |  | G | 2015-03-12 | 2015-03-19 | 2015-03-26 | 2015-04-02 | 2015-04-09 | 2015-04-16 | 2015-04-23 | 2015-04-30 | 2015-05-07 | 2015-05-14 | 2015-05-21 | 2015-05-28 | 2015-06-04 | 2015-06-11 | 2015-06-18 | 2015-06-25 | 2015-07-02 | 2015-07-09 | 2015-07-16 | 2015-07-23 | 2015-07-30 | 2015-08-06 | 2015-08-13 | 2015-08-20 | 2015-08-27 | 2015-09-03 | 2015-09-10 | 2015-09-17 | 2015-09-24 | 2015-10-01 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-05 | 2015-11-12 | 2015-11-19 | 2015-11-26
Manageable Issues / Risks |  |  | Y
Major Problems |  |  | R
Project Scope |  |  |  | G | G | G
Resources |  |  |  | G | G | G
Timeline |  |  |  | G | G | Y
Project Finance |  |  |  | G | G | G
Risks & Issues |  |  |  | G | G | Y
Overall Project Health |  |  |  | G | G | Y
Latest Achievements / Completed Tasks
Project Kickoff and Onsite Survey
Educational Training
SOP Meeting
Open Issues and Risks
Description | [14 empty] | Rating |  | Responsibility | [5 empty] | Planned Actions
WH Floor Maintenance | [16 empty] | Setra | [5 empty] | Setra team is waiting feedback from maintenance company
Racking Readiness | [16 empty] | Setra | [5 empty] | Setra team is waiting feedback from racking company
Major Activities for the Next Period | [19 empty] | Milestones in the next 6 Months
RF Devices Readiness estimated date: dd/mm/yyyy | [19 empty] | Description | [16 empty] | Date
WH Access Points (Connection) Readiness estimated date: dd/mm/yyyy | [19 empty] | Project Kick-Off | [16 empty] | 2015-02-08
Labels Printers Readiness estimated date: dd/mm/yyyy | [19 empty] | SOP signoff by Setra | [16 empty] | 2015-04-02
Have all items barcoded | [19 empty] | UAT phase signoff | [16 empty] | 2015-05-07
Get all the received pallets dimensions | [19 empty] | Go-Live execution | [16 empty] | 2015-05-17
Try to get all items dimensions and volumes | [19 empty] | Go-Live phase signoff | [16 empty] | 2015-05-25
Prepare the location labels after furnishing the warehouse and setting the final locations