## Check List
Task | Related To | Task Description | Responsibility | Latest Date | Status | Must Be Completed Before | Comments | Client
1 | General Requirements | Identify and select the Super-Users team, 2 Operational Resources and one IT WMS System Administrator. | Client |  | Open | UAT |  | SNS
2 | General Requirements | Update SNS on the Super-Users profile and roles in the warehouse operation. | Client |  | Open | UAT |  | Client/SNS
3 | General Requirements | Master Data validation: Location, Zones, SKU, Packkeys Optional: Pick Faces Assignment - Slotting | Client |  | Open | UAT
4 | General Requirements | "Product Knowledge" session, given by the client team to the team leader and/or floor operators | Client |  | Open | UAT
5 | General Requirements | Make sure the RF Devices and the Wireless Infrastructure / Access Points providors are commited for on-site presense and support during the UAT phase. | Client |  | Open | UAT
6 | General Requirements | Make sure the RF Devices and the Wireless Infrastructure / Access Points providors are commited for on-site presense and support during the Go-Live phase. | Client |  | Open | Go-Live
7 | Warehouse Readiness | Racking System installed in all areas and chambers | Client |  | Open | Go-Live
8 | Warehouse Readiness | Location Labels printed and affixed on all locations | Client |  | Open | Go-Live
9 | Warehouse Readiness | MHE ready and operational (Forklift, Pallets Woods…) | Client |  | Open | Go-Live
10 | Warehouse Readiness | Warehouse operators and labor recruited and trained on driving the MHE. | Client |  | Open | Go-Live
11 | IT Readiness | The Remote Connection should be established and tested between the Test server and the SNS offices. | Client/SNS |  | Open | UAT
12 | IT Readiness | LAN cabling and connection to be extended to the warehouses and connected to the Main Office network. | Client |  | Open | UAT
13 | IT Readiness | Ensure that WMS Live / Production Servers and Workstations are operational | Client |  | Open | Go-Live
14 | IT Readiness | Ensure the readiness of a Project Room for the SNS & Client staff on site with A/C and Internet Connection | Client |  | Open | UAT
15 | IT Readiness | Ensure that all third party software are installed on the Live / Production server and workstations (Refer to WMS Software Requirement sheet) | Client |  | Open | Go-Live
16 | IT Readiness | RF and Access Points readiness: Ensure RF coverage in all areas of the warehouse and test all RF terminals. | Client |  | Open | UAT
17 | IT Readiness | RF devices equipped with Telnet Client application | Client |  | Open | UAT
18 | IT Readiness | Labels and Other Printers installed and configured | Client |  | Open | UAT
19 | IT Readiness | Disaster Recovery Plan for: • RF Failure • Server Down time • Database corruption | Client |  | Open | Go-Live
20 | IT Readiness | Daily Backup procedure defined and in place | Client |  | Open | Go-Live
21 | Training & Superuser Readiness | Readiness of the Training Room (Projector, White Board, Markers) | Client |  | Open | UAT
22 | Training & Superuser Readiness | Test Server + one Workstation per participant | Client |  | Open | UAT
23 | Training & Superuser Readiness | All Software Requirement installed on Training Server and Work-Stations and network connection established | Client |  | Open | UAT
24 | Training & Superuser Readiness | Sufficient numbers of Super-Users compared to initial plan and agreement | Client |  | Open | UAT
25 | Training & Superuser Readiness | Super-Users to be exclusively assigned to the "Go Live". Managers to sign off commitment. Unless special circumstances exist, no key players will be allowed leave during Go Live as well as the month prior to and after Go Live. | Client |  | Open | Go-Live
26 | Training & Superuser Readiness | UAT Training: • 3 to 4 days Super-Users training • 1 day Exception Handling training • 2 day Super-users train End User • 1 day practicing on Real transactions | Client/SNS |  | Open | Go-Live
27 | Training & Superuser Readiness | Super-Users and End Users evaluation and readiness: • Check UAT issues and users questions • SOP defined by Super-Users and transferred in full to End users | Client/SNS |  | Open | Go-Live
28 | Training & Superuser Readiness | WMS system Administrator assigned and training on: • WMS client connectivity and language.ini • RF connectivity and prompts overview • Overview on WMS Database structure • WMS version Deployment • Security Administration | Client/SNS |  | Open | Go-Live
29 | WMS Test Environment | WMS User Profiles, Logins and Access rights | SNS |  | Open | Go-Live
30 | WMS Test Environment | Master Data verification and upload on WMS. Results of data audit will feed into "Go/No Go" decision. | Client/SNS |  | Open | Go-Live
31 | WMS Test Environment | RF Devices setup properly • Auto Logon • Full Screen • Keyboard Short cuts | Client/SNS |  | Open | Go-Live
32 | Interface Testing & Technical Handover | Interface full cycle Testing between WMS and Host | Client/SNS |  | Open | Go-Live
33 | Interface Testing & Technical Handover | Client to confirm SOP processes and Integration details readiness for the Go-live | Client |  | Open | Go-Live
34 | Interface Testing & Technical Handover | BOOMI IP Manager training and handover: • Running and Scheduling Interfaces • Viewing Logs • Fixing Errors | Client/SNS |  | Open | Go-Live
35 | Physical Stock Count | Warehouse Operation to be stopped for X number of Days - Provision for buffer Stock, informing Storers/Clients before hand | Client |  | Open | Go-Live
36 | Physical Stock Count | Planning of Stock Counts Teams during full Physical Count duration. Stock Count teams are not allowed leave. | Client |  | Open | Go-Live
37 | Physical Stock Count | Stock count and Go-Live teams should be fully dedicated to the task No Pending transactions or unfinished shipments If Host/ERP exists, all transactions should be closed. A snap shot of the Stock quantities should be uploaded as Expected ASN in the WMS | Client |  | Open | Go-Live
38 | Physical Stock Count | All stocks should be in their storage locations. Pending stock should be moved aside and marked as ‘Not to Count’ | Client |  | Open | Go-Live
39 | Physical Stock Count | If Host/ERP exists: Adjustment of Host or ERP stock levels should be prepared and approved by required management level | Client |  | Open | Go-Live
40 | Physical Stock Count | Storers or 3PL Clients participating in Physical count planning and informed in advance of Go-live possible constraints: • Delay in Stock Count and Reconciliation • Delay in Picking/Shipping processes | Client |  | Not Applicable | Go-Live
41 | Go-Live Environment | Production Environment: verify Database, Server, RF setup, Work-stations, final WMS settings If Integration exists, change connection to Production Environment | SNS |  | Open | Go-Live
42 | Go-Live Environment | WMS Configuration: Lottable Validation - Cartonization - System Flags - Putaway Strategies - Slotting - Billing Flag - PICKTO Move Flag in Case of Paper Based Picking | Client/SNS |  | Open | Go-Live
43 | Go-Live Environment | Gather Data about Expected transaction volume on 1st day of Go-live | Client/SNS |  | Open | Go-Live
44 | Go-Live Environment | Plan with Super-Users team and delegate supervisory tasks on different operational activities | Client/SNS |  | Open | Go-Live
45 | Go-Live Environment | Pallet / Drop ID labels printed and ready | Client |  | Open | Go-Live
46 | Go-Live Environment | In case of Drop in productivity on "Go Live", to bring more Key users and helpers on the floor. | Client |  | Open | Go-Live
47 | Go-Live Environment | Change Control process: • Functional modifications requested in the WMS will be logged, reviewed and completion schedule agreed upon • Urgent changes will be reviewed, developed and tested by Super-users • New Report requests will be logged, reviewed and completion schedule agreed upon | Client/SNS |  | Open | Go-Live
48 | Super User Readiness | Sufficient testing has been done on system: • Weekly checks on transactions by SNS shows that super users have been working on the system and completed enough transactions | Client |  | Open | Go-Live | To be validated by SNS