## Weekly Status Report (2)
|  | Project Name | [5 empty] | Takhzeen SCE10.3 Implementation | [5 empty] | SNS Project Manager |  |  |  | Charbel Azzi | Report Date | 2015-06-01 | Project Plan / Progress Snapshot
|  | Operational Consultant | [5 empty] | Mario Hadid | [5 empty] | SNS Business Manager |  |  |  | Wael Mabsout
Project Phases |  |  |  | Status |  |  |  |  | Project Highlights
I | Project Initiation |  |  | Completed |  |  |  |  | Kick- Off , Education trianing and SOP workshop finalized on 21/05/2015
II | Business Review Summit |  |  | In Progress |  |  |  |  | SNS to send SOP document by 4/06/2015
III | Design and Development |  |  | Not Started |  |  |  |  | It was agreed that Takhzeen will go-live with Godiva Storer
IV | Deployment and UAT |  |  | Not Started
V | Go-Live |  |  | Not Started
VI | Project Closure |  |  | Not Started
Project Health Indicators |  |  |  | Period Ending
On Track |  |  | G | 2015-05-17 | 2015-05-19 | 2015-05-21 | 2015-06-02 | 2015-06-07 | 2015-07-01 | 2015-07-19 | 2015-08-02
Manageable Issues / Risks |  |  | Y
Major Problems |  |  | R
Project Scope |  |  |  | G | G | G
Resources |  |  |  | G | G | G
Timeline |  |  |  | G | G | Y
Project Finance |  |  |  | G | G | G
Risks & Issues |  |  |  | G | G | G
Overall Project Health |  |  |  | G | G | G
Latest Achievements / Completed Tasks | [14 empty] | Date Completed
Kick-Off Meeting | [14 empty] | 2015-05-17
Educational Training | [14 empty] | 2015-05-19
SOP Workshop | [14 empty] | 2015-05-21
Open Issues and Risks
Description | [11 empty] | Rating | Responsibility |  |  |  | Planned Actions
Delay in phase 4 if Hardware(Wifi hotsports and Servers) not avaibale | [11 empty] | High | Customer |  |  |  | Customer to obtain Hardware servers
Location Labels not ready on warehouse racks | [11 empty] | High | Customer |  |  |  | Customer to prepare Location labels in Chamber 23
RF handhelds not available | [11 empty] | Medium | Customer |  |  |  | Customer to obtain RF handheld and provide SNS delivery date
Major Activities for the Next Period | [15 empty] | Milestones in the next 6 Months
SOP Sign-Off Document | [15 empty] | Description |  |  |  | Estimated Date
[16 empty] | SOP Sign-Off |  |  |  | 2015-06-07