## Weekly Status Report (2)
|  | Project Name | [5 empty] | Takhzeen SCE10.3 Implementation | [5 empty] | SNS Project Manager |  |  |  | Charbel Azzi | Report Date | 2015-06-09 | Project Plan / Progress Snapshot
|  | Operational Consultant | [5 empty] | Mario Hadid | [5 empty] | SNS Business Manager |  |  |  | Wael Mabsout
Project Phases |  |  |  | Status |  |  |  |  | Project Highlights
I | Project Initiation |  |  | Completed |  |  |  |  | Kick- Off , Education trianing and SOP workshop finalized on 21/05/2015
II | Business Review Summit |  |  | In Progress |  |  |  |  | Delivery of final version of the SOP will be delayed due to delay in Exceptional Scenario's list from Takhzeen
III | Design and Development |  |  | Not Started |  |  |  |  | Servers and other required hardware are still not ordered.
IV | Deployment and UAT |  |  | Not Started |  |  |  |  | Updated project plan will be sent due to delay in server readiness and exceptional scenarios
V | Go-Live |  |  | Not Started
VI | Project Closure |  |  | Not Started
Project Health Indicators |  |  |  | Period Ending
On Track |  |  | G | 2015-05-17 | 2015-05-19 | 2015-05-21 | 2015-06-02 | 2015-06-07 | 2015-07-01 | 2015-07-19 | 2015-08-02
Manageable Issues / Risks |  |  | Y
Major Problems |  |  | R
Project Scope |  |  |  | G | G | G | G
Resources |  |  |  | G | G | G | G
Timeline |  |  |  | G | G | Y | Y
Project Finance |  |  |  | G | G | G | G
Risks & Issues |  |  |  | G | G | G | G
Overall Project Health |  |  |  | G | G | G | G
Latest Achievements / Completed Tasks | [14 empty] | Date Completed
Kick-Off Meeting | [14 empty] | 2015-05-17
Educational Training | [14 empty] | 2015-05-19
SOP Workshop | [14 empty] | 2015-05-21
Open Issues and Risks
Description | [11 empty] | Rating | Responsibility |  |  |  | Planned Actions
Delay in phase 4 if Hardware(Wifi hotsports, handhaleds and Servers) not avaibale | [11 empty] | High | Takhzeen |  |  |  | Takhzeen to obtain Hardware servers
Location Labels not ready on warehouse racks | [11 empty] | High | Takhzeen |  |  |  | Takhzeen to prepare Location labels in Chamber 23
Delay in SOP sign off | [11 empty] | High | Takhzeen |  |  |  | Takhzeen to send exceptional scenarios that needs to be incorporated in SOP
Major Activities for the Next Period | [15 empty] | Milestones in the next 6 Months
SOP Sign-Off Document | [15 empty] | Description |  |  |  | Estimated Date
[16 empty] | SOP Sign-Off |  |  |  | TBD